## Sheet1
Old Server (Top4 Jails)	Status	Responsible	New Infrastructure (VMs)	Beta Available	Switch to Production	Comment
mail.uugrn.lan	pending	Sur5r	mail.uugrn.org
mx1.uugrn.org	pending	Sur5r	mail.uugrn.org
mysql.uugrn.lan	will be discontinued		-			will be deployed on VMs that need it.
proxy.uugrn.lan	will be discontinued		-
shell.uugrn.lan	beta active	Zugschluss	shell.uugrn.org	2020-02-18	2020-05-22	shell.new.uugrn.org is up
uugrn.uugrn.lan (web)	pending	Anna	www.uugrn.org			{www|fixme|stammtisch|wiki}.uugrn.org
uugrn.uugrn.lan (dns)	pending	Zugschluss	dns.uugrn.org			depends on dwalin (Mail send @ 2020-04-23)
uugrn.uugrn.lan (vorstand)	done	Sdk	vorstand.uugrn.org		2020-05-02
irc.uugrn.lan	beta active	Sdk	irc.uugrn.org	2020-03-21	2020-05-30	irc.new.uugrn.org is up
cgiirc.uugrn.lan	will be discontinued		-
bnc.uugrn.lan	limited beta	Sdk	irc.uugrn.org	2020-04-30	2020-05-30
xmpp.uugrn.lan	pending	Sdk	chat.uugrn.org			conflicts with jitsi on the same VM
wiki2.uugrn.lan	pending	Anna	www.uugrn.org
lists.uugrn.lan	pending	Sur5r	mail.uugrn.org
blogs.uugrn.lan	pending	Flow	blogs.uugrn.org
pad.uugrn.lan	pending	Andi	-
news.uugrn.lan	to be clarified		-			anyone up to do it? (mile?)
acme.uugrn.lan	will be discontinued		-
cloud.uugrn.lan	pending	Flow	cloud.uugrn.org
mile.uugrn.lan	tbd	Mile	mile.uugrn.org
mile23.uugrn.lan	tbd	Mile	mile.uugrn.org
rabe.uugrn.lan	will be discontinued		-
trickster.uugrn.lan	tbd	Trickster	trickster.new.uugrn.org
che.uugrn.lan	tbd	Che	che.uugrn.org
pb.uugrn.lan	tbd	Pb	pb.uugrn.org
arslan.uugrn.lan	tbd	Arslan	arslan.uugrn.org
flow.uugrn.lan	tbd	Flow	flow.uugrn.org
andi.uugrn.lan	tbd	Andi	andi.uugrn.org
schwede.uugrn.lan	tbd	Schwede	schwede.uugrn.org
-	done	Sdk	chat.uugrn.org		2020-03-21